|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ASHFIELD DISTRICT COUNCIL LOCAL PLAN 2023-2040** | | | **Ashfield District Council Logo** |  |
|  |  |  |  |  |
| **Identification of further sites for allocation in accordance with the submitted plan’s spatial strategy to meet housing needs**  **Timetable** | | | | |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **ID** | **Task Name** | **Start** | **Finish** | **Jan** | **Feb** | **Mar** | **Apr** | **May** | **June** | **July** |
| 1 | Identification of further sites for allocation | Jan | Jan |  |  |  |  |  |  |  |
| 2 | Local Plan Development Committee. Seek recommendation for proposed changes | Feb | Feb |  |  |  |  |  |  |  |
| 3 | Update Local Plan documents | Feb | Feb |  |  |  |  |  |  |  |
| 4 | Cabinet: Seek approval for proposed changes and for Public Consultation | Feb | Feb |  |  |  |  |  |  |  |
| 5 | Full Council: Seek approval for proposed changes and for Public Consultation | Feb | Feb |  |  |  |  |  |  |  |
| 6 | Public consultation on proposed changes (6 weeks) | Feb | April |  |  |  |  |  |  |  |
| 7 | Consider responses and prepare a Consultation Statement | April | April |  |  |  |  |  |  |  |
| 8 | Local Plan Development Committee. Seek recommendation for consultation Statement and additional sites | May | May |  |  |  |  |  |  |  |
| 9 | Cabinet: Seek approval for consultation Statement and additional sites, and to submit documents to the Inspector | May/ June | May/ June |  |  |  |  |  |  |  |
| 10 | Full Council: Seek approval for consultation Statement and additional sites, and to submit documents to the Inspector | May/ June | May/ June |  |  |  |  |  |  |  |
| 11 | Submit documents to Inspectors | June | June |  |  |  |  |  |  |  |

10.01.2025